Project Scope Summary

| Category | Details |
| --- | --- |
| Web Pages | 6 Pages (Homepage, About, Services, Blog, Careers, Contact) |
| CMS | Strapi Headless CMS |
| Design | Based on Figma (ลูกค้าจัดเตรียม) |
| Hosting | AWS (EC2) |
| Features | Blog, Case Studies, Contact Form |

Project Timeline

| Phase | Duration | Activities | Deliverables |
| --- | --- | --- | --- |
| Phase 1: Discovery & Planning | 1 Week | Requirement Analysis, Tech Setup, Figma Review | Project Plan |
| Phase 2: Design Review | 1-2 Weeks | Figma Review, Design Adjustments, Component Planning | Approved Design |
| Phase 3: Frontend Development | 2 Weeks | Next.js Development, Component Building, Responsive Design | Working Frontend |
| Phase 4: Backend & CMS | 1.5 Weeks | Strapi Setup, Content Types, API Integration | CMS Ready |
| Phase 5: Integration | 1 Week | Frontend-Backend Integration, Contact Form | Integrated System |

## Manday Estimation by Requirement

### 1. Website Structure (Frontend Pages)

| Page | Features | Frontend | Backend | QA | Mandays |
| --- | --- | --- | --- | --- | --- |
| Homepage | Hero, Introduction, Featured content, CTA (Static page) | 3 | 0.5 | 0.5 | 4 |
| About Page | Brand Story, Philosophy, Who We Are, Leadership, Values (Static page) | 3 | 0.5 | 0.5 | 4 |
| Services Page | 3 Service categories, 10 Industries list (Dynamic page) | 2.5 | 0.5 | 0.5 | 3.5 |
| Blog/Insights/News | Article listing, Search/Filter, Categories (Dynamic page) | 3 | 1 | 0.5 | 4.5 |
| Case Study Layout | Challenge, Strategy, Execution, Results, Gallery (Static page) | 2.5 | 1 | 0.5 | 4 |
| Careers Page | Culture, Values, Open positions list (Dynamic page) | 2 | 0.5 | 0.5 | 3 |
| Contact Page | Contact form, Office details, Map (Static page) | 2 | 0.5 | 0.5 | 3 |
| Subtotal (Pages) |  |  |  |  | 26 |

### 2. Backend Requirements (CMS & API)

| Requirement | Description | Backend | Frontend | QA | Mandays |
| --- | --- | --- | --- | --- | --- |
| CMS Setup & Integration | Strapi installation, Configuration | 2 | 0 | 0.5 | 2.5 |
| Blog/Insights CMS | Create/Edit/Schedule posts, Categories/Tags | 2 | 1 | 0.5 | 3.5 |
| Services CMS | Service descriptions, Industries list | 1 | 0.5 | 0.25 | 1.75 |
| Careers CMS | Add/Remove job postings | 1 | 0.5 | 0.25 | 1.75 |
| Subtotal (Backend) |  |  |  |  | 9.5 |

### 3. Infrastructure

| Task | Description | DevOps | Backend | Mandays |
| --- | --- | --- | --- | --- |
| Docker Setup | Containerization (Frontend + CMS) | 1 | 0.5 | 1.5 |
| AWS Infrastructure | VPC, EC2 | 2 | 0 | 1.5 |
| Monitoring Setup | CloudWatch, | 0.5 | 0 | 0.5 |
| Subtotal |  |  |  | 3.5 |

Pricing

Payment Terms

| Milestone | Percentage | Amount (THB) | Trigger |
| --- | --- | --- | --- |
| 1. Project Kickoff | 30% | ฿ | ลงนามสัญญา |
| 2. Design Approval | 20% | ฿ |  |
| 3. Development Complete | 30% | ฿ | Frontend + CMS Ready |
| 4. Go-Live | 20% | ฿ | Website Live |
| Total | 100% | ฿ |  |

Terms & Conditions

- Scope Changes: การเปลี่ยนแปลง Scope จะต้องผ่าน Change Request และอาจมีค่าใช้จ่ายเพิ่มเติม

- Payment: Invoice จะถูกส่งตาม Milestone และมีเครดิต 15 วัน

- Warranty: รับประกันแก้ไข Bug ฟรี 30 วันหลัง Go-Live

- Cancellation: หากยกเลิกโปรเจค ค่าใช้จ่ายที่เกิดขึ้นแล้วจะไม่คืน

- Confidentiality: ข้อมูลทั้งหมดจะถูกเก็บเป็นความลับ